## Sheet1
deliverable | school | size | description | quantity | delivery info | status | programming | code
Poster | University of ND | 8 1/2 x 11 | ENG | 25 | 8/17 Delivery to: University of North Dakota Career Services Attn: Nancy Nelson (Hess Corp Event Posters) 2891 2nd Ave. North, Stop 9014 MaCannel Hall, Rm 280 Grand Forks, ND 58202 | production |  | AP40013200
Poster | CSM | 11 x 17 | GEO | 10 | 8/28 (address in cell 28B) | 7/27 EB approved |  | AP40013200
Poster | CSM | 11 x 17 | ENG | 10 | 8/28 (address in cell 28B) | 7/27 EB approved |  | AP40013200
Poster | Montana Tech | 11 x 17 | ENG | 12 | 8/17 (address in cell 28C) | 7/28 EB approved |  | AP55065
Poster | University of Utah | 11 x 17 | GEO | 3 | 9/1 (address in cell 28 G) | 8/3 EB approved |  | AP40013200
Poster | Texas A&M | 11 x 17 (need confirmation) | GSC | TBD | TBD due date and address | Awaiting clarity from client |  | AP40011050
Poster | Texas A&M | 11 x 17 | GEO | 20 | September 16 (address in cell 28F) | 7/28 EB approved |  | AP40013200
Poster | ASU | 11 x 17 (need confirmation) | GSC | TBD | TBD due date and address | Awaiting clarity from client |  | AP40011050
Poster | MSU | 11 x 17 (need confirmation) | GSC | TBD | TBD due date and address | Awaiting clarity from client |  | AP40011050
E Blast | University of ND |  | ENG |  |  | Sent back to Olo on 8/3 for revision |  | AP40013200
E Blast | Texas A&M |  | GEO |  |  | mechanicals |  | AP40013200
E Blast | Texas A&M |  | GSC |  |  | Awaiting clarity from client |  | AA40011050
E Blast | ASU |  | GSC |  |  | Awaiting clarity from client |  | AP40011050
E Blast | MSU |  | GSC |  |  | Awaiting clarity from client |  | AP40011050
E Blast | Montana Tech |  |  |  |  | Create using poster info |  | AP55065
Profile | Elizabeth | 8 1/2 x 11 | Geologist |  |  | Completed & Printed
Profile | Elizabeth | 8 1/2 x 11 | Geologist |  |  | Completed & Printed
Profile | Chao | 8 1/2 x 11 | Geophysicist |  |  | Completed & Printed
Profile | Greg | 8 1/2 x 11 | Geologist |  |  | Completed & Printed
Profile | Kendra | 8 1/2 x 11 | Engineer |  |  | Completed & Printed
Profile | Randy | 8 1/2 x 11 | Engineer |  |  | Completed & Printed
| Colorado School of Mines Career Center Attn: Debbie Behnfield (Hess Corporation Posters) Ben Parker Student Center 1600 Maple Street, STE 37 Golden, CO 80401 | Montana Tech Career Services Attn: Hess Corp Interviews URC 109 1300 West Park Street Butte MT 59701 |  |  | Texas A&M University Dept. of Geology & Geophysics Attn: Suzanne Rosser- Hess Recruiting Material TAMU 3115 Room 101 Halbouty College Station, TX 77843 | University of Utah - Geology & Geophysics Attn: Dustin Porlas Frederick Albert Sutton Bldg 115 S 1460 East Room 383 Salt Lake City, UT 84112